# BSOD IPEX MOZAMBIQUE

# EM module

Place			Maputo, Mozambique

Date			July 07-11, 2008

Program manager	Mrs. Anneke Wevers

External experts	Mr. Hans Verhulst, CEE , Mrs. Phoebe Owuor, EE pilot project coordination, Ms. Dorothy Tuma, EE content management, Mr. F.J. Koekoek, EE agro-sector

- Project nr		B.5.192.2.001

- Executive summary

- General outline

- Given the nature of the supply base of Mozambique, the institutional EM program has been built around a parallel process of EU export capacity building and pilot projects. Both incorporate elements of export development and export promotion. IPEX selected the pilot projects from existing projects and programs, based on criteria set by itself and third party local stakeholders. An innovative feature of the program is the individual mentoring process, facilitated by a group of external experts with diverse expertise under strict parameters (n=1; R=G). An important contribution to the program is the involvement of the EKN in kind and funds.

- Activities

- Selection of pilot projects towards a long list and preparation of IPEX staff on export project management. Lining up and organization of external expert-team with adequate expertise. Seeking involvement of local stakeholders and international donors in the program. Objectives of the BSOD/EM program were set, a road map was made with participants, the process of conversion towards a short list for PP’s initiated, an outline of the export process flow explained and basic market research techniques discussed. Planning was specified till Dec 31. First pilot projects can be completed by May-June 2009. Preliminary results of the sessions are creation of ownership towards the program and willingness to actively contribute; familiarity with the participatory approach, basic knowledge on approach in export services and on task related market research for the pilot projects.

- Participants

- Participants came from various backgrounds with diverse experience in exports, from just over a month, to over 19 years.  They began the week eagerly. When introduced to the participatory approach they showed initial resistance and scepticism.  However, by the end of the week, all participants were comfortable with the approach and were actively engaged with the process.

- Pilot projects

- The whole process of designing working methods, organization structure and Selection Criteria of “PP” that looked quite challenging in the beginning was overcome through a systematic and tactful approach by the “EEs. This ensures high probability of success with the “PP” as total ownership of the project was evident among the participants. We used their ideas and thoughts and turned these into actionable.

- Organization

- Preparation and logistical support by IPEX was excellent. Some minor issues need to be addressed with Hotel Cardoso for future events.

- Introduction

- In this –the first- report on the EM module we have extensively reported on past activities as well so as to present a coherent report on the underlying reasons for the content and approach of the program.

- General outline

- The general outline of the programme follows our recommendations on tailor made learning cycles by addressing diverse needs and speeds of people in learning about export marketing to the EU and boosting institutionalisation of the gained experience.

- This EM module got off to a flying start by exposing participants to communicating in English and discussing basic and strategic issues of the export process, while assigning them immediately to put their knowledge and skills in practice.

- The general outline of the program is designed around a two parallel processes, i.e. identification, selection and implementation of export pilot projects to the EU on one hand and the transfer of underlying theory, best practices and general principles related to each step of the pilot project process. The pilot projects are leading in the programme, thus making the transfer of knowledge and skills depending on the speed and sequence of steps in the pilot projects.

- The pilot projects replace the carrier company projects from earlier EM modules. There were two dominant reasons for this replacement

- Lack of consistent and quality supply from Mozambique for EU markets, which created the need for multi-source supply projects.

- Tendency of BSO’s to shift focus of carrier company projects to trade generation rather than institutional development of their organization.

- From here till the end of 2008 the following diagram will be the backbone of the EMM module

- On the left are the practical steps in the export process as used for the pilot projects, on the right the related underlying theory and general principles that are relevant for and in each step. The long list of pilot projects have been selected from

- the product groups, that are not included in the “95/10” i.e. 95% of all Mozambican export effectuated by 10 companies - all base commodities (left upper box of diagram)

- Product groups, that are subject of existing national or international programs or projects that can be linked international trade (right upper box of diagram).

- Observations on primary demand – supply base

- The long list, which is the basis for the selection of pilot project in the coming months, currently contains 20 products, from each of the major regions of the country: North, Central and South. The products are distributed over the following product groups: fresh fruit and vegetables (9 products); edible nuts and oil seeds (5 products); other natural ingredients (4 products) and non-food (2 products: handicrafts and furniture). 5 task teams were formed to assess the potential of  each of the products on the long list: two teams for fresh fruit and vegetables and one for each of the other groups.

- Focusing on the food products, we have two main categories of products: fresh fruit and vegetables, which are perishable and therefore place high demands on logistics, and natural ingredients, which have a longer shelf life and are therefore easier to handle. Nevertheless, fulfilling quality requirements will be challenging enough also for this category.

- Two observations seem relevant: a mission of CBI external expert Piet Schotel on fresh fruit and vegetables found that exports of this category to Europe are still very small. Especially for SMEs it will be hard to overcome the logistical challenges associated with exporting to Europe. Only two companies currently export to Europe, one using air freight (via Johannesburg) to export vegetables, the other exporting grapefruit by ship through the Fresh Produce Terminal in Maputo (owned by Capespan). Once several banana and mango projects come of age this situation may improve. However, small production volumes, demand from the SA market, quality and logistics are major bottlenecks for export to Europe. On the other hand, seasonality and availability of land and labour are favourable factors.

- Concerning the natural ingredients on the long list, there has been discussion about whether or not these have the nature of commodities. The product consultant’s view on this is that each of these products may be considered a (minor) commodity.  They are more or less standardised products traded in global markets. However, this does not exclude the possibility of adding value. Whether labelled ingredients or commodities, these products are generally differentiated according to origin, type, grade, quality and other aspects including service. This is a difference related to production and primary processing. More advanced value adding options (related to secondary processing or producing finished products) may also be present, but are generally much more difficult to realise. The commodity nature of these products means that prices are dictated by the market and subject to volatility, while the differentiation implies that a “quality differential” may be obtained depending on the characteristics of the product and production process. It will be hard to find meaningful export alternatives in a predominantly agricultural country like Mozambique to agricultural commodities.

- Activities - past

- Before this intervention, during formulation of the EM module, the idea rose to use pilot projects as the backbone of the capacity building, given the fact that the supply base from Mozambique for products to the EU is rather erratic. Some criteria for these pilot projects were discussed with IPEX management, like

  - realistic expectations on market access compliance

  - potential to add value to commodity based products

  - opportunities to invite other stakeholders in the export value to participate.

- Discussion were held with a number of stakeholders to seek their interest and participation: Cepagri, Olipa, Innoq, Frutisul/Frutimel, CTA, Technoserve, USAID, DNC, a/o.  A special role in this process was taken up by EKN, which showed interest in co-financing of the projects and contribute with suggestions for other projects.

- Within the framework of the SP module, IPEX staff members were asked to compile the necessary information to produce a long list of potential pilot projects (PP’s) , in combination with a list of existing business development programs in Mozambique. With this information the first long list of projects was constructed. Parallel to that, workshops were held on project management to prepare the IPEX staff for the upcoming tasks in the preparation and implementation of the PP’s.

- A task team was formed with the objective to

  - facilitate a tailor made program for the IPEX project teams while working on the PP’s, taking into account the diverse and different needs and speeds that PP teams would be requiring (see Prahalad: n=1;R=G)

  - enable proper linkage of practice and theory to secure the institutional development within IPEX and in its network with other stakeholders.

  - Provide the necessary sector-related expertise and market demand issues in the EU.

- Mr. Freek Jan Koekoek was asked to coordinate and implement the EU- and sector specific transfer of knowledge and provide assistance through LDC to the PP teams. He will use specific expertise of other experts when necessary.

- Mrs. Phoebe Owuor (Kenya) was asked to coordinate the process and sequence of steps of the PP through frequent meetings with individual PP-teams and LDC.

- Ms. Dorothy Tuma (Uganda) was asked to coordinate transfer of knowledge, necessary for implementation of each step of the PP’s. She has conducted a baseline TNA and will anticipate training needs before each step of the PP. Implementation will take place through frequent workshops with individual PP-team, keeping an eye on efficiency by combining workshop-sessions whenever possible, and LDC.

- Activities – present

- Activities and results

- This week’s sessions included the following activities:

- Discuss the primary and secondary objectives of the BSOD/EM program

- Construct a road map with participants for the program

- Complete the process of conversion towards a short list for PP’s

- Discuss the basic outline of the export process flow

- Provide sufficient insight in market research techniques

- Detailed planning of activities till Sep 01 and outline for planning till Dec 31.

- Preliminary results of the sessions were

- Ownership towards the program and willingness to contribute

- Full awareness from the part of participants on knowledge/skills requirements

- Familiarity with the participatory approach

- Basic knowledge on approach in export services

- Basic knowledge on PP task related market research

- Subjects covered - working methods

- Subjects covered were as follows:

- The export process flow, crossroads and hurdles, need for assistance – Following a brief introduction to the export process flow to be used throughout the programme, participants worked in groups to develop and present their own ideas on the steps involved in the export process flow, crossroads, hurdles and need for assistance.  This was the participant’s first fully participatory exercise, which also served to give the external experts an insight into participant familiarity with the export process. One power point slide showing the export process flow was shown to participants periodically throughout the week, for emphasis.

- Introduction to market research – In a highly interactive presentation, participants received an overview of the elements of market research they would need to be familiar with in order to effectively narrow down the long list of projects to a short list of 5 – 7 pilot projects.

- Project management, working methods – Working in groups, participants discussed and agreed on the working methods they would use in reducing the number of projects on the long list to the short list.

- Project management, organization – Participants determined the manner in which they would organize themselves in order to implement the task at hand.  Group sizes and member roles were defined, group members were randomly assigned to groups and each group selected a group leader (see Attachment III).

- Project management, criteria for selection – Working in groups, participants determined the criteria to be used in narrowing down the long list of 22 products to a short list of 5 – 7 pilot projects.  Participants worked together to consolidate the criteria from each of the groups into a single final list with 6 selection criteria.

- Introduction to finding data on the internet – One of the participants gave an on-line demonstration to introduce participants to on-line sources of information on the EU market e.g. the CBI Website and several of ITC’s Tools e.g. Trade Map, Product Map etc.

- Setting up a market research plan for selection of pilot projects – Working in the groups listed in Attachment III, participants prepared a deliberate Action Plan for the tasks they will undertake from July 2008 – September 2008.

- By the close of the week, one participant had been identified to present a training module (at the next plenary session) on Comparative and Competitive Advantages, which appeared to be a point of confusion among participants.  As other training needs are identified over the next few weeks, at least two other participants will be invited to present training modules at the next plenary.  Participants giving presentations will receive coaching from the CBI Regional Experts.

- The goal was to facilitate the capture of existing knowledge from among the participants.  This was successfully achieved with participants agreeing that they were indeed responsible for defining the parameters they would be working under during the pilot project selection process.

- Participants

- Knowledge and progress

- “Our people should be more exposed to these types of programs” was Mr. Macaringue’s (President of IPEX) first reaction after sitting in one morning in the first leg of the EM program. It quickly became clear –confirming the signals from the baseline diagnostics - that we were dealing with a group of people that need to be taken back to a basic structured approach towards export development and export promotion. Some of the participants have been exposed to similar programs, like the traditional CBI seminars in Rotterdam, but all of them lacked the experience of actually using the knowledge and applying the skills required in ED and EP.

- A long and challenging journey has started, but all team members are confident that the group will be able to exceed initial expectations.

- There is a clearly noticeable language barrier, which put a brake on the communication during the week. In combination with the participatory methodology which was strictly applied during plenary sessions, this resulted in  uneasiness, long silences and confusion during the first day and part of the second day. Thanks to excellent work of the external experts from Uganda and Kenya, we managed to break this atmosphere and by the end of the week, real discussions started to emerge. Here again, a long journey awaits, but participants themselves indicated that they are eager to improve their communication skills in English and with this attitude the main hurdle for our program has been taken. During group sessions, discussions in native language was encouraged.

- In total, 28 persons attended the sessions, including the “invitados” from IPEX and third party stakeholders, which all played an active role in the proceedings.

- It was encouraging to see that IPEX management –in spite of other priority issues like attending an incoming Italian mission, municipality elections and oversees travel schedules participated in the program whenever their schedules allowed them to do so. We feel this is probably the most positive contribution to this first meeting, which is more than anything the “tone-setter” from the entire program. (see Annex II for list of participants)

- Efforts to evaluate the knowledge level of participants prior to Week I through a baseline test proved unsuccessful, owing to the fact that several of the participants copied their answers to the test from a single script.  Both right and wrong answers were duplicated in numerous instances.  It was also clear from the answers on the scripts that some of the questions had not been properly understood.  This could be attributed to the fact that the participants are more comfortable with Portuguese than they are with English.

- Through in-class observation however, it was clear that a wide range of knowledge was represented in the room.  Participants ranged from over 19 years in export to just over one month.  Additionally, some participants were there simply to broaden their understanding of the institution they work for e.g. Lawyers and Human Resource Personnel.

- Ultimately, English did not prove to be a problem and all feedback from participants indicates that the week exceeded their expectations.  All participants should feel comfortable with the level of knowledge and skills attained in each of the covered subjects (listed above), primarily because a participatory, action-based approach was used.  Although initially viewed with scepticism by those who had expected to attend lectures all week, by the end of the week all participants had begun to feel comfortable with the approach.

- Pilot projects

- Objectives

- The objectives of the “PP” are and not limited to the following:

- Serve as a methodology for capacity building to Ipex and other stakeholders

- Serve as success stories and testimonials for Ipex and other stakeholders

- Through a selection criteria process replace the long list with a short list after rigorous selection criteria

- Maybe facilitate in the process some formidable Value Chains

- Eventually open up some EU markets for Mozambique products

- Activities

- Four  groups outlined and shared their thought processes on “PP” working methods

- Approaches and structure of groups. The 4 presentations were merged and condensed into one agreeable methodology. Similarly 4 groups developed “PP” selection criteria which were eventually merged through elimination into one list of six selection criteria (S.Cs) as listed below. Selection of team members was easy as democracy was applied. However, the team leader’s election/selection was the most challenging as usual in Africa-no one wanted to take responsibility. We had to apply a lot of wisdom and skills to get round this challenge. The elimination and merging of the products for S.C purposes was equally easy and acceptable.

- Can we comply with market access requirements?

  - Standards, norms, time to comply

- Can we meet market demands ?

  - Customer values, prices

- Is there sufficient potential to add value ?

  - Technology (production, marketing)

- Does infrastructure permit timely deliveries ?

  - Time, frequency, convenience, risks

- Is supply sufficient and diverse ?

  - Volumes, number of suppliers

- Can the project be implemented within budget ?

  - < USD 50.000

- Results achieved

- A designed export process approach

- Framework of ‘PP’ working methodology

- A workable organizational structure design for pp teams

- An agreed upon selection criteria for the ’PP’ by team members

- Selection of team members and leaders through consensus

- Confirmation of commitment by both leaders and members

- Acceptance of short-term immediate action plan

- Pending matters short term

- Distribution of tasks among team members of ‘PP’

- Drawing up of action plans for each team

- Designing approach and intervention plan

- Invitation of other stakeholders

- Activities - next

- Start of work on PP		July 11

- Progress reporting		weekly till Aug 29

- Internal analysis			July 11 – July 30

- Review session			End of July

- External analysis			July 11- Aug 15/20

- Submission of final list		Aug 26	Discussions on final list IPEX/CBI/Donors

- Decision of short list		Aug 29	IPEX management

- Formal launch of program	Sep 01		FACIM

- Plenary session			Sep 15-19 	PP formulation/proposal

- or	Sep 29-Oct 02

- Completion of financing PP	Oct. 31, 2008	PP team sessions

- Missions Mrs. P. Owuor (3-4)	till Dec 31	On PP process progress

- Missions Ms. D. Tuma (3-4)	till Dec 31	On EM content

- Plenary session			Dec 1-5 	Completion of Export Audit

- Organization

- The sessions were held in Hotel Cardoso, sponsored by USAID. Preparations for the sessions were handled excellently by IPEX and logistical assistance during the meetings was equally good. The hotel did not comply with all agreements made, this will be dealt with separately in coordination with IPEX and USAID.

- Recommendations

- Due to the timeframe of the project the EEs need to be at hand to guide, coach and encourage the pp teams

- During the proposal draw-up we need to include the VCDA where applicable

- The ‘PP’ selection process is critical and needs all the attention-its the mother of our success-it requires consolidated efforts from us all

- Hans Verhulst

- Phoeb Owuor

- Dorothy Tuma

- Freek Jan Koekoek

- July 2008

- Attachment I

- Program schedules

- Attachment II

- List of participants and attendance

- Attachment III – projects list

Attachment III

Evaluation of workshop at IPEX 8 – 11 July 2008

Eduardo: supports the method, they could come out with ideas, methods, steps. Anything to improve? “Nothing”.

Antonio (external): subject (i.e. export promotion) was out of my background, but useful, especially info on value chains. Looks forward to next sessions. Methodology very good, given different backgrounds. Language constraints have been interfering, but faculty have dealt with it.

Calima: was able to consolidate his knowledge. Working method: the best way, learning by doing. On the external analysis, especially market access requirements, he would like to learn more. (This is actually foreseen in the program.) Also, he welcomes more team bonding and team work.

Jose: learnt about the concept of “crossroads”.

Marlene (external): good invitation, good method, we can learn more by doing

Laurene: we have been given a task.

Elisa: very important to attend part of the seminar.

Nurene (external): thanks IPEX and CBI. Content real good. Methodology practical and hands-on. We will strengthen ourselves, especially leadership and teambuilding capacity. Wants to know more about market access requirements. Asks the group how we can develop capacities and skills to meet EU standards. We need to organise ourselves. Learnt that most of the export promotion activity is planning / preparing for exports.

Rita: good week. Work method useful. Good to work more together.

Cecilia: starting point. We need commitment to dig the gold.

Flavia: good. Could consolidate information. She felt part of the process, a player. That felt better than merely receiving lectures.

Octavio: hopes that we will  help to capitalize on this week. That is will not end now. Together we can do the job.

… Useful to improve her market research activity. Positive.

Wetela: congratulates the team. All of us gained. Thanks to different people.

Vania. Was worried the first day. Today she must confess: she learnt many things. Especially about working in groups. Now comes the hard work.

Rabecca: good week. Learnt more about export market. Final step to implement pilot projects.

Adilson (Frutimel): good, as first step for a producer to learn about exports. Enjoyed the method.

Favian: good to learn from participants. Improved knowledge about searching European market.

Prahalad, 2007, The new age of innovation, Wiley’s and Son, New York.